## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Data Engineer | 2025-09-22 | Null values in loan_amount column not handled | Sprint 1 | Backend Team | Logical | Added null-handling logic | 2025-10-06 | closed | All records now handled
2 | Data Scientist | 2025-10-07 | Incorrect encoding of categorical gender field | Sprint 2 | DS Team | Standards | Corrected encoding function | 2025-10-20 | closed | Compliance with data standards
3 | Data Scientist | 21-10-2025 | Features mismatch between training and prediction input | Sprint 3 | DS Team | Maintainability | Synchronized feature lists | 2025-11-03 | closed | Better code maintainability
4 | Frontend Dev | 2025-11-04 | No input validation on Streamlit income fields | Sprint 3 | Frontend Team | User Interface | Added type & value validation | 2025-11-17 | closed | Improved UX
5 | Backend Dev | 2025-11-18 | Flask API crashes on special characters in email signup | Sprint 4 | Backend Team | Logical | Implemented regex validation | 2025-12-01 | closed | Prevented crashes

## Sheet2
Logical
User Interface
Maintainability
Standards
Others