## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As an ML engineer, I want to clean and preprocess the loan dataset so that it can be used for model training. | Must Have | Raw dataset | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | As an ML engineer, I want to build and evaluate the ML model for loan eligibility prediction. | Must Have | Cleaned dataset | Backend Team | Completed
Sprint 1 | Sprint 1 | US003 | As an ML engineer, I want to save the trained model as a .pkl file so that other services can use it. | Should Have | Trained model | Backend Team | Completed
Sprint 2 | Sprint 2 | US004 | As a frontend developer, I want to build a basic Streamlit UI for entering loan details. | Must Have | Model ready | Frontend Team | Completed
Sprint 2 | Sprint 2 | US005 | As a frontend developer, I want to integrate the Gemini AI chatbot into Streamlit for user queries. | Should Have | Gemini API | Frontend Team | Completed
Sprint 2 | Sprint 2 | US006 | As a user, I want an interactive interface that shows clear results (Approve/Reject). | Must Have | Streamlit forms | Frontend Team | Completed
Sprint 3 | Sprint 3 | US007 | As a backend developer, I want to create Flask APIs for prediction using the saved ML model. | Must Have | Model file | Backend Team | Completed
Sprint 3 | Sprint 3 | US008 | As a backend developer, I want to implement secure user authentication (signup/login). | Must Have | DB planned | Backend Team | Completed
Sprint 3 | Sprint 3 | US009 | As a developer, I want to integrate Streamlit UI with Flask APIs to connect frontend & backend. | Should Have | Flask endpoints | Both Teams | Completed
Sprint 4 | Sprint 4 | US010 | As a database engineer, I want to create MySQL tables for Users and LoanApplications using SQLAlchemy ORM. | Must Have | DB server | Backend Team | Completed
Sprint 4 | Sprint 4 | US011 | As a backend developer, I want prediction history to be automatically stored in the database. | Should Have | Database ready | Backend Team | Completed
Sprint 4 | Sprint 4 | US012 | As a user, I want my login and prediction history to load properly through the UI. | Should Have | DB + UI integration | Both Teams | Completed
Sprint 4 | Sprint 4 | US013 | As a developer, I want end-to-end integration between UI, backend, chatbot, and database. | Must Have | All components | Both Teams | Completed